ASTRA RUNTIME

Project Bible

Capability-Based Cybersecurity-Hardened Userspace Runtime for Linux

| Field | Value |
| --- | --- |
| Version | 0.1.0-dev (Codename: foundation) |
| Platform | Linux x86-64 (GCC 13+ / Clang 17+) |
| Language | C++23 with x86-64 Assembly |
| Repository | https://github.com/KernelArch-Lab/Astra |
| Owner | Shiva (bshivaramakrishnan@gmail.com) |
| Status | Pre-alpha, architecture-defining phase |
| Date | April 2026 |

# Table of Contents

1. Project Overview & Repository

2. Architecture — 6 Layers, 21 Modules

3. How the Runtime Works

4. What Has Been Built (Current State)

5. Git History & Branch Strategy

6. Naming Conventions & Code Standards

7. Build System & Toolchain

8. Module Sprint Plans (10 Sprints Each)

8.1  M-01 Core Runtime

8.2  M-02 Isolation Layer

8.3  M-03 IPC Engine

8.4  M-04 Checkpoint

8.5  M-05 Replay

8.6  M-06 Memory Allocator

8.7  M-07 Job Engine

8.8  M-08 AI Scheduler

8.9  M-09 eBPF Telemetry

8.10 M-10 WASM Sandbox

8.11 M-11 AQL Query Language

8.12 M-12 Verification Engine

8.13 M-13 Network Stack

8.14 M-14 Virtual Filesystem

8.15 M-15 Consensus Engine

8.16 M-16 Hardware Abstraction

8.17 M-17 Profiler

8.18 M-18 Crypto Engine

8.19 M-19 Virtual Time

8.20 M-20 Module Loader

8.21 M-21 Assembly Core

9. Integration Map & Cross-Module Dependencies

10. Implementation Order (Phased Roadmap)

11. What Remains To Be Built

12. Critical Context for New Sessions

# 1. Project Overview & Repository

Astra Runtime is a modular, capability-based, cybersecurity-hardened, AI-augmented userspace runtime for Linux x86-64. It implements a microkernel-inspired architecture where 21 modules communicate exclusively through IPC, mediated by unforgeable capability tokens. Every resource access — memory allocation, process spawning, filesystem I/O, network connections — requires a valid capability token with the appropriate permission bits.

## Core Design Principles

No Heap Allocation in Hot Path — all critical resources pre-allocated at init time.

Capability-Based Security — every resource access mediated by unforgeable 128-bit tokens.

Microkernel Architecture — modules communicate via IPC, never direct function calls.

Extensibility via Hooks — ProcessManager has HookRegistry for intervention points.

Zero-Copy Where Possible — IPC uses memfd, allocator uses pre-allocated pools.

Defense in Depth — seccomp, namespaces, poison patterns, auditing, CFI.

Thread-Safe Primitives — spinlock protection, atomic state reads, lock-free publish.

Compile-Time Configuration — sanitizers, log levels, CPU features determined at build.

Deterministic Lifetime — no surprise OOM; all memory budgets controlled upfront.

Observability-First — event bus + audit hooks + per-module logging.

## Repository Details

| Item | Value |
| --- | --- |
| GitHub URL | https://github.com/KernelArch-Lab/Astra |
| Organisation | KernelArch-Lab |
| Default Branch | main |
| License | Proprietary (private repo) |
| CI/CD | GitHub Actions (planned) |
| Primary Language | C++23 |
| Secondary | x86-64 Assembly (NASM) |
| Build System | CMake 3.28+ |
| Target OS | Linux only (kernel 5.15+) |
| Target Arch | x86-64 with AES-NI, SHA-NI, RDRND, SSE4.2, AVX2 |

# 2. Architecture — 6 Layers, 21 Modules

Astra follows a layered architecture where higher layers depend on lower layers but never the reverse. Each module implements the IService interface, registers with the ServiceRegistry, and communicates through the EventBus and IPC channels.

| Layer | Modules | Purpose |
| --- | --- | --- |
| Layer 6: Infrastructure | M-13 Network, M-14 Filesystem, M-18 Crypto, M-19 Virtual Time, M-20 Module Loader | Platform services that modules use for I/O, cryptography, and dynamic loading. |
| Layer 5: Application | M-07 Job Engine, M-10 WASM, M-11 AQL, M-15 Consensus, M-17 Profiler | User-facing services: job scheduling, sandboxed WASM execution, query language, distributed consensus. |
| Layer 4: Intelligence | M-08 AI Scheduler, M-16 HAL (Hardware Abstraction) | ML-based scheduling decisions, hardware feature detection and abstraction. |
| Layer 3: Security | M-12 Verification Engine | Formal verification of runtime invariants, policy enforcement. |
| Layer 2: Services | M-02 Isolation, M-03 IPC, M-04 Checkpoint, M-05 Replay, M-09 eBPF | Core services: sandboxing, inter-process communication, state persistence, observability. |
| Layer 1: Core | M-01 Core Runtime, M-06 Allocator, M-21 ASM Core | Foundation: capability model, service registry, process management, memory allocation, crypto primitives. |

## Complete Module Registry

| ID | Name | Layer | Status | Description |
| --- | --- | --- | --- | --- |
| M-01 | Core Runtime | Layer 1 | ACTIVE (Phase 2) | Capability model, ServiceRegistry, ProcessManager, EventBus, HookRegistry |
| M-02 | Isolation Layer | Layer 2 | ACTIVE (Sprint 1) | Linux namespace sandboxing, seccomp profiles, Landlock |
| M-03 | IPC Engine | Layer 2 | PARTIAL | Zero-copy IPC via memfd, CAZC protocol |
| M-04 | Checkpoint | Layer 2 | PLANNED | Process state snapshots for migration/recovery |
| M-05 | Replay | Layer 2 | PLANNED | Deterministic replay from checkpoint data |
| M-06 | Memory Allocator | Layer 1 | ACTIVE (Sprint 3) | 4-tier pool allocator, quotas, audit, capability-gated |
| M-07 | Job Engine | Layer 5 | PLANNED | Task scheduling, DAG execution, priority queues |
| M-08 | AI Scheduler | Layer 4 | PLANNED | ML-based resource scheduling, learned heuristics |
| M-09 | eBPF Telemetry | Layer 2 | PLANNED | Kernel-level observability, syscall tracing |
| M-10 | WASM Sandbox | Layer 5 | PLANNED | WebAssembly execution in sandboxed environment |
| M-11 | AQL Query | Layer 5 | PLANNED | Astra Query Language for runtime introspection |
| M-12 | Verification | Layer 3 | PLANNED | Formal verification of invariants and policies |
| M-13 | Network Stack | Layer 6 | PLANNED | Capability-gated networking, firewall rules |
| M-14 | Virtual Filesystem | Layer 6 | PLANNED | Sandboxed filesystem with capability checks |
| M-15 | Consensus | Layer 5 | PLANNED | Distributed consensus for multi-node Astra |
| M-16 | HAL | Layer 4 | PLANNED | Hardware detection, CPU feature abstraction |
| M-17 | Profiler | Layer 5 | PLANNED | Runtime profiling, flame graphs, hotspot analysis |
| M-18 | Crypto Engine | Layer 6 | PLANNED | TLS, key management, hardware-accelerated crypto |
| M-19 | Virtual Time | Layer 6 | PLANNED | Deterministic time for replay and testing |
| M-20 | Module Loader | Layer 6 | PLANNED | Dynamic module loading with signature verification |
| M-21 | ASM Core | Layer 1 | ACTIVE (Stubs) | x86-64 asm: secure wipe, constant-time compare, RDRAND |

# 3. How the Runtime Works

## Boot Sequence

main() parses CLI arguments (-n name, -v verbose, -V version).

Signal handlers installed for SIGINT/SIGTERM (async-safe requestShutdown).

RuntimeConfig constructed with name, log level, max services/processes.

Runtime::init() executes 6-stage pipeline: Platform checks -> ASM self-test -> CapabilityManager -> EventBus -> ServiceRegistry -> ProcessManager.

Root capability token created with ALL permissions (the 'god token').

Services register via ServiceRegistry (topological sort resolves dependencies).

Runtime::run() enters main event loop — dispatches events, reaps children, enforces restart policies.

On SIGINT/SIGTERM: requestShutdown() sets atomic flag, run() exits loop.

Runtime::shutdown() stops services in reverse dependency order.

## Capability Token System

Every operation in Astra requires a CapabilityToken — a 128-bit unforgeable identifier paired with a Permission bitmask. Tokens form derivation chains: a derived token can only have a subset of its parent's permissions (monotonic narrowing). The CapabilityManager supports atomic epoch-based revocation — incrementing the epoch invalidates all tokens created before it, in O(1) time.

Permission categories (66 bits defined):

| Category | Permissions |
| --- | --- |
| Service | SVC_REGISTER, SVC_LOOKUP, SVC_UNREGISTER |
| IPC | IPC_SEND, IPC_RECV, IPC_CREATE_CHAN |
| Process | PROC_SPAWN, PROC_KILL, PROC_INSPECT |
| Memory | MEM_ALLOC, MEM_MAP |
| Filesystem | FS_READ, FS_WRITE, FS_EXEC |
| Network | NET_CONNECT, NET_LISTEN, NET_RAW |
| System | SYS_ADMIN, SYS_AUDIT, SYS_MODULE_LOAD, SYS_SHUTDOWN |

## Service Lifecycle

All modules implement IService with: name(), moduleId(), onInit(), onStart(), onStop(), isHealthy(), getDependencies(). The ServiceRegistry holds up to 64 services in pre-allocated slots with O(1) lookup by ModuleId. Registration triggers dependency graph construction with topological sort and cycle detection. Services start in dependency order and stop in reverse.

## Process Spawning Pipeline

ProcessManager manages up to 256 processes with real Linux fork/exec. Each ProcessDescriptor holds: PID, platform PID, capability token, isolation profile, restart policy, restart count, and last exit code. States: EMPTY -> CREATED -> SPAWNING -> RUNNING -> STOPPED/CRASHED.

Spawn sequence with hooks:

PRE_SPAWN hooks execute (capability validation, resource checks).

fork() creates child process.

POST_FORK hooks execute in child (namespace setup via M-02 Isolation).

execve() replaces child image with target binary.

POST_SPAWN hooks execute in parent (register with eBPF, start monitoring).

On exit: PRE_KILL / POST_EXIT hooks fire; restart policy evaluated.

## Event Bus

Lock-free ring buffer with 1024 entries, each 64-byte cache-aligned. Events carry: type (U16), source module ID, sequence number, nanosecond timestamp, and a union payload. Up to 64 subscribers per event type. Dispatch happens synchronously from the main loop thread. Module-specific events start at MODULE_EVENT_BASE = 1000, with 100 IDs reserved per module.

## Memory Allocation Pipeline

AllocatorService::allocateFor() implements a 5-stage security pipeline: (1) verify MEM_ALLOC capability, (2) check per-module quota, (3) route to appropriate pool tier via MemoryManager, (4) emit audit event, (5) return result. On failure at any stage, quotas are released and the appropriate audit event type is emitted (CAPABILITY_REJECT, QUOTA_REJECT, POOL_EXHAUSTED).

Four-tier pool architecture:

| Tier | Block Size | Max Blocks | Total Memory | Use Case |
| --- | --- | --- | --- | --- |
| Small | 64 B | 4,096 | 256 KB | Tokens, small structs, metadata |
| Medium | 256 B | 2,048 | 512 KB | Messages, configs, buffers |
| Large | 1,024 B | 512 | 512 KB | Larger buffers, serialized data |
| Page | 4,096 B | 128 | 512 KB | Page-aligned data, DMA buffers |

# 4. What Has Been Built (Current State)

## M-01 Core Runtime — Phase 1 + Phase 2 Complete

The Core Runtime is the most mature module. Phase 1 delivered: CapabilityManager (4096 tokens, spinlock-protected creation, lock-free validation, epoch-based revocation), ServiceRegistry (64 slots, topological sort, cycle detection), ProcessManager (256 slots, fork/exec, restart policies: NEVER/ALWAYS/ON_FAILURE/EXPONENTIAL), EventBus (1024-entry ring buffer, 64 subscribers per type, lock-free publish). Phase 2 added: HookRegistry (5 HookPoints with priority ordering), dependency graph with topological sort, real fork/exec integration, and comprehensive test suites.

Key files:

include/astra/core/capability.h — CapabilityToken, Permission enum (66 bits), CapabilityManager

include/astra/core/service.h — IService interface, ServiceRegistry (64 slots)

include/astra/core/process.h — ProcessManager, ProcessDescriptor, RestartPolicy

include/astra/core/event_bus.h — EventBus, EventType enum, 64-byte aligned Event

include/astra/core/hook.h — HookRegistry, HookChain, 5 HookPoints

include/astra/core/runtime.h — Runtime orchestrator, init/run/shutdown pipeline

include/astra/core/logger.h — Per-module file-backed Logger

src/core/ — 8 implementation files (runtime.cpp, capability.cpp, etc.)

## M-02 Isolation Layer — Sprint 1 Complete

Sprint 1 delivered: ProfileEngine with 5 sandbox profiles (PARANOID, STRICT, STANDARD, RELAXED, CUSTOM), NamespaceManager for Linux USER + PID namespace creation with UID/GID mapping, ScopedFd RAII wrapper, and IsolationService that registers as a ProcessManager isolation hook. State machine: INIT -> USER_CREATED -> MAPPED -> PID_CREATED -> ACTIVE with atomic transitions and rollback on failure.

## M-06 Memory Allocator — Sprint 1-3 Complete

Sprint 1: Pool-based allocation with intrusive freelist, 4-tier routing (Small/Medium/Large/Page), zero-on-free via volatile memset, spinlock thread safety. Sprint 2: Poison fill patterns (0xAB alloc, 0xDE free), status markers (0xAC allocated, 0xFE freed), double-free detection, corruption checks, foreign pointer rejection, DeallocResult enum (OK/DOUBLE_FREE/FOREIGN_PTR/NULL_PTR/NOT_INITIALISED). Sprint 3: QuotaManager with per-module byte budgets and underflow tracking, AllocAuditor with 8 event types (ALLOC, FREE, QUOTA_REJECT, DOUBLE_FREE, FOREIGN_PTR, CORRUPTION, CAPABILITY_REJECT, POOL_EXHAUSTED), AllocatorService implementing IService with capability-gated allocateFor().

## M-21 Assembly Core — Stubs Active

C++ fallback stubs are in place for: asmSecureWipe (volatile memset), asmConstantTimeCompare (constant-time byte comparison), asmRandomU64 (RDRAND instruction), asmLfence (lfence barrier). These stubs are NOT production-hardened — the real x86-64 assembly implementations are planned for Sprint 2+.

## Common Infrastructure

types.h: Fixed-width types (U8-U64, I8-I64), ModuleId enum (21 modules), ProcessId, ServiceId, kMaxModules=32, kMaxProcesses=256. result.h: ErrorCode enum (40+ codes), ErrorCategory (5 categories), Result<T> template, Status type. version.h: ASTRA_VERSION_MAJOR/MINOR/PATCH, codename, feature flags. log.h: Header-only lightweight logger. platform.h: Linux/x86-64 compile-time validation, CPU feature detection.

## Test Suite Summary

| Test Suite | File | Assertions | Status |
| --- | --- | --- | --- |
| Allocator Sprint 1 | test_pool_allocator.cpp | 65 | ALL PASS |
| Allocator Sprint 2 | test_sprint2_hardening.cpp | 72 | ALL PASS |
| Allocator Sprint 3 | test_sprint3_security.cpp | 114 | ALL PASS |
| Core Phase 2 | test_phase2.cpp | Multiple | ALL PASS |
| Isolation Sprint 1 | test_sprint1_namespace.cpp | Multiple | ALL PASS |
| Phase 2 Verification | 5 test files in phase2_verify/ | Multiple | ALL PASS |

Total across allocator suites: 251 assertions, all passing.

# 5. Git History & Branch Strategy

## Commit History

| Hash | Message |
| --- | --- |
| 8cf4c98 | fix(M-06): Address code review — audit event types, underflow tracking, CMake targets |
| 3e57f5c | feat(M-06): Sprint 3 — Per-module quotas, capability gating, audit hooks |
| 8c05ec6 | feat(M-06): Sprint 2 — Poison patterns, double-free detection, corruption checks |
| ed39ffe | feat(M-06): Sprint 1 — Pool-based memory allocator with 4-tier routing |
| 9e3e444 | Sprint1 (isolation initial) |
| c257f6e | Merge PR #2 — M-02 Sprint 1 namespace manager |
| ba3542d | Merge PR #4 — M-01 Phase 2 core |
| 74b7c20 | feat(M-01): Phase 2 — real fork/exec, dependency graph, hook registry |
| 8c284c2 | fix(M-02): code review fixes + PID namespace double-fork fix |
| eb308e0 | feat(M-02): Sprint 1 — ProfileEngine + NamespaceManager |
| 5f5fee5 | feat(M-03): Zero-Copy IPC Engine (CAZC-IPC) |
| 75d4a51 | Add Single Global Logger class |
| 6c0966c | Implement Core module (M-01): capability model, service registry, event bus, process mgr |
| 91fd831 | Initial commit: project structure, build system, main entry point |

## Branch Strategy

| Branch | Purpose |
| --- | --- |
| main | Stable integration branch — all PRs merge here |
| feature/m01-phase2-core | M-01 Phase 2 development (merged) |
| feature/m02-isolation-sprint1 | M-02 Isolation Sprint 1 (merged) |
| feature/m02-sprint1-namespace-manager | M-02 namespace manager (merged) |
| feature/m06-sprint1-allocator | M-06 Sprint 1 (merged) |
| feature/m06-sprint2-hardening | M-06 Sprint 2 (merged) |
| feature/m06-sprint3-security | M-06 Sprint 3 (merged) |
| remotes/origin/Branch-Laakhi | Laakhi's initial implementation |
| remotes/origin/m03-ipc-engine-srivatsan_k | M-03 IPC by Srivatsan |
| remotes/origin/observability | Observability branch |

Convention: feature/<module>-<sprint>-<description>. PRs to main require code review. Direct pushes to main for hotfixes only.

# 6. Naming Conventions & Code Standards

The project enforces a strict Hungarian-inspired naming convention across all C++ code. This is non-negotiable and must be followed in every file.

| Prefix | Meaning | Examples |
| --- | --- | --- |
| m_ | Member variables | m_iCount, m_szName, m_vItems, m_bEnabled |
| l | Local variables | liResult, lszMessage, lbDone |
| a | Function arguments | aiCount, aSzPath, aBEnabled |
| i | int / signed integer | m_iValue, liIndex |
| u | unsigned integer | m_uSize, luCount |
| f | float | m_fWeight |
| d | double | m_dPrecision |
| c | char | m_cDelimiter |
| sz | string (std::string/string_view) | m_szName, aSzPath |
| b | bool | m_bEnabled, lbDone |
| v | vector | m_vItems |
| p | pointer | m_pBuffer, aPNode |
| e | enum | m_eState, aEModule |
| arr | array | m_arrUId |
| fn | function/callback | m_fnCallback |
| r | reference | aRConfig |

## Additional Standards

C++23 standard required (C++17 polyfills for test environments with older compilers).

All warnings are errors (-Werror -Wall -Wextra -Wpedantic).

Security hardening flags always on (stack protector, FORTIFY_SOURCE, PIE, RELRO).

No heap allocation in hot paths — pre-allocate everything at init.

Spinlocks preferred over mutexes for short critical sections.

Atomic operations for lock-free read paths.

volatile memset for security-critical memory wiping.

Every module implements IService interface.

Header-only where possible for core types and templates.

# 7. Build System & Toolchain

## Requirements

| Tool | Minimum Version | Notes |
| --- | --- | --- |
| CMake | 3.28+ | Build system generator |
| GCC | 13+ | Primary compiler (C++23 support) |
| Clang | 17+ | Alternative compiler |
| Linux Kernel | 5.15+ | For namespace/seccomp/eBPF features |
| NASM | 2.15+ | x86-64 assembly (future) |

## Build Commands

| Action | Command |
| --- | --- |
| Configure (Debug) | cmake -B build -DCMAKE_BUILD_TYPE=Debug . |
| Configure (Release) | cmake -B build -DCMAKE_BUILD_TYPE=Release . |
| Build | cmake --build build -j$(nproc) |
| Run Tests | cd build && ctest --output-on-failure |
| With ASan+UBSan | cmake -B build -DASTRA_ENABLE_SANITIZERS=ON . |
| With TSan | cmake -B build -DASTRA_ENABLE_TSAN=ON . |
| With Coverage | cmake -B build -DASTRA_ENABLE_COVERAGE=ON . |
| Run Runtime | ./build/astra_runtime -n AstraNode1 -v |
| Run Demo | ./build/astra_demo |

## Build Presets

| Preset | Flags | Use |
| --- | --- | --- |
| debug | Assertions, debug symbols | Development |
| release | O2/O3, hardening | Production |
| sanitize | ASan + UBSan | Memory/UB bug finding |
| fuzz | libFuzzer instrumentation | Security testing |

## Active CMake Targets

| Target | Type | Dependencies |
| --- | --- | --- |
| astra_core | Static library | astra_asm_core |
| astra_asm_core | Static library | None |
| astra_isolation | Static library | astra_core |
| astra_allocator | Static library | astra_core |
| astra_runtime | Executable | astra_core, astra_asm_core, pthread, dl |
| astra_demo | Executable | astra_core, astra_asm_core, pthread, dl |
| test_allocator | Test (CTest) | pthread |
| test_allocator_sprint2 | Test (CTest) | pthread |
| test_allocator_sprint3 | Test (CTest) | pthread |

## Known Build Environment Note

The Cowork VM runs Ubuntu 22.04 ARM with g++11, which lacks C++23 support. A C++17-compatible shim for std::expected exists at /tmp/shim2/expected for test compilation in that environment. The user's Mac has g++13+ / Clang 17+ and builds the full project natively.

# 8. Module Sprint Plans (10 Sprints Each)

Each module follows a progression from foundation to production-ready. Early sprints build standalone functionality; later sprints integrate with other modules, add security hardening, performance optimization, and comprehensive testing.

## 8.01  M-01 Core Runtime

The central nervous system of Astra. Manages capabilities, services, processes, events, and hooks.

| Sprint | Title | Details | Dependencies |
| --- | --- | --- | --- |
| Sprint 1 [DONE] | Foundation | CapabilityToken struct, Permission enum, CapabilityManager with spinlock, create/validate/revoke | None |
| Sprint 2 [DONE] | Service Registry | IService interface, ServiceRegistry with 64 slots, O(1) lookup, lifecycle callbacks | Sprint 1 |
| Sprint 3 [DONE] | Event Bus | EventBus with 1024-entry ring buffer, lock-free publish, subscriber dispatch | Sprint 1 |
| Sprint 4 [DONE] | Process Manager | ProcessManager with 256 slots, fork/exec, ProcessState machine, restart policies | Sprint 1-3 |
| Sprint 5 [DONE] | Hook Registry | HookRegistry, HookChain, 5 HookPoints, priority ordering, dependency graph | Sprint 4 |
| Sprint 6 | Epoch Revocation | Batch revocation, revocation callbacks, cascading revoke for derived tokens | Sprint 1 |
| Sprint 7 | Service Health | Health check framework, automatic restart of unhealthy services, circuit breaker | Sprint 2,4 |
| Sprint 8 | Event Persistence | Durable event log, replay from log, event compaction | Sprint 3, M-04 |
| Sprint 9 | Multi-Node Runtime | Remote service discovery, distributed capability validation | Sprint 2, M-13, M-15 |
| Sprint 10 | Production Hardening | Stress testing, formal verification of capability invariants, performance tuning | All prior |

## 8.02  M-02 Isolation Layer

Linux namespace-based sandboxing with seccomp, Landlock, and cgroup resource limits.

| Sprint | Title | Details | Dependencies |
| --- | --- | --- | --- |
| Sprint 1 [DONE] | Namespace Foundation | USER + PID namespace creation, UID/GID mapping, ScopedFd RAII, ProfileEngine with 5 profiles | M-01 |
| Sprint 2 | Seccomp Integration | BPF-based syscall filtering, per-profile allow/deny lists, audit mode | Sprint 1 |
| Sprint 3 | Landlock Filesystem | Landlock LSM rules for filesystem access control per process | Sprint 2 |
| Sprint 4 | Cgroup Resource Limits | Memory, CPU, PID limits via cgroups v2, enforcement per profile | Sprint 1 |
| Sprint 5 | Network Namespaces | veth pair creation, bridge networking, loopback isolation | Sprint 1, M-13 |
| Sprint 6 | Mount Namespace | Isolated mount points, bind mounts, tmpfs overlays | Sprint 1 |
| Sprint 7 | Profile Composition | Custom profiles from combining base profiles, runtime profile modification | Sprint 1-6 |
| Sprint 8 | Isolation Metrics | Track syscall denials, resource limit hits, namespace failures via EventBus | Sprint 1-7, M-09 |
| Sprint 9 | Hot Migration | Move process between isolation profiles without restart | Sprint 1-8, M-04 |
| Sprint 10 | Production Hardening | Fuzz seccomp filters, verify namespace escape prevention, benchmark overhead | All prior |

## 8.03  M-03 IPC Engine

Zero-copy inter-process communication using memfd and capability-gated channels.

| Sprint | Title | Details | Dependencies |
| --- | --- | --- | --- |
| Sprint 1 | Channel Foundation | memfd-based shared memory channels, IpcChannel struct, create/destroy | M-01 |
| Sprint 2 | Message Protocol | CAZC (Capability-Authenticated Zero-Copy) message format, header/payload | Sprint 1 |
| Sprint 3 | Send/Receive | Blocking and non-blocking send/recv, futex-based signaling | Sprint 1-2 |
| Sprint 4 | Capability Gating | IPC_SEND/IPC_RECV permission checks on every message | Sprint 1-3, M-01 |
| Sprint 5 | Channel Directory | Named channels, lookup by name or ModuleId, automatic cleanup | Sprint 1-4 |
| Sprint 6 | Multicast | One-to-many channels, subscriber groups, fan-out delivery | Sprint 5 |
| Sprint 7 | Flow Control | Backpressure, credit-based flow control, queue depth monitoring | Sprint 3 |
| Sprint 8 | Message Serialization | Zero-copy serialization framework, schema validation | Sprint 2 |
| Sprint 9 | Cross-Node IPC | TCP/Unix socket transport for multi-node Astra, message routing | Sprint 1-8, M-13 |
| Sprint 10 | Production Hardening | Benchmark throughput/latency, fuzz message parsing, stress test channels | All prior |

## 8.04  M-04 Checkpoint

Process state snapshots for migration, recovery, and time-travel debugging.

| Sprint | Title | Details | Dependencies |
| --- | --- | --- | --- |
| Sprint 1 | Snapshot Foundation | Capture process memory, register state, fd table to file | M-01, M-06 |
| Sprint 2 | Incremental Snapshots | Track dirty pages, only snapshot changed regions | Sprint 1 |
| Sprint 3 | Filesystem State | Capture open files, file positions, pending I/O | Sprint 1, M-14 |
| Sprint 4 | IPC State | Snapshot in-flight IPC messages, channel state | Sprint 1-3, M-03 |
| Sprint 5 | Checkpoint Storage | Compressed storage, deduplication, retention policies | Sprint 1-4 |
| Sprint 6 | Restore Pipeline | Reconstruct process from checkpoint: memory, fds, IPC channels | Sprint 1-5 |
| Sprint 7 | Live Migration | Move running process to different node via checkpoint/restore | Sprint 6, M-13 |
| Sprint 8 | Checkpoint Triggers | Periodic, event-driven, manual checkpoint triggers | Sprint 1-7 |
| Sprint 9 | Verification | Checksum verification, checkpoint integrity validation | Sprint 5, M-12 |
| Sprint 10 | Production Hardening | Benchmark checkpoint/restore latency, test with large processes | All prior |

## 8.05  M-05 Replay

Deterministic replay from checkpoint data for debugging and forensics.

| Sprint | Title | Details | Dependencies |
| --- | --- | --- | --- |
| Sprint 1 | Replay Foundation | Load checkpoint, replay syscall results from recorded log | M-04 |
| Sprint 2 | Syscall Recording | Intercept and record all syscall return values and side effects | Sprint 1, M-09 |
| Sprint 3 | Deterministic Scheduling | Replay thread scheduling decisions, lock acquisition order | Sprint 2, M-19 |
| Sprint 4 | I/O Replay | Replay network and filesystem I/O from recorded data | Sprint 3, M-13, M-14 |
| Sprint 5 | Time Travel | Forward and backward stepping through execution | Sprint 1-4 |
| Sprint 6 | Breakpoints | Set replay breakpoints on events, syscalls, memory access | Sprint 5 |
| Sprint 7 | Divergence Detection | Detect when replay diverges from recording, report cause | Sprint 1-6 |
| Sprint 8 | Partial Replay | Replay single module while simulating others from log | Sprint 1-7, M-03 |
| Sprint 9 | Forensic Analysis | Post-mortem replay of crashed processes, root cause analysis | Sprint 8, M-04 |
| Sprint 10 | Production Hardening | Verify replay determinism, benchmark overhead of recording | All prior |

## 8.06  M-06 Memory Allocator

4-tier pool-based allocator with quotas, audit, and capability-gated access.

| Sprint | Title | Details | Dependencies |
| --- | --- | --- | --- |
| Sprint 1 [DONE] | Pool Foundation | PoolAllocator<BlockSize,MaxBlocks> template, intrusive freelist, zero-on-free | None |
| Sprint 2 [DONE] | Hardening | Poison fill (0xAB/0xDE), status markers, double-free detection, corruption checks | Sprint 1 |
| Sprint 3 [DONE] | Security | QuotaManager, AllocAuditor (8 event types), AllocatorService (IService), capability gating | Sprint 2, M-01 |
| Sprint 4 | Slab Allocator | Variable-size allocation via slab classes, best-fit selection | Sprint 1-3 |
| Sprint 5 | Huge Pages | 2MB/1GB huge page support for large allocations, THP management | Sprint 4 |
| Sprint 6 | NUMA Awareness | Per-NUMA-node pools, locality-aware allocation | Sprint 5, M-16 |
| Sprint 7 | Memory Pressure | OOM handling, memory pressure notifications, graceful degradation | Sprint 3 |
| Sprint 8 | Learned Allocator | ML-based allocation prediction, prefetching, adaptive tier sizing | Sprint 1-7, M-08 |
| Sprint 9 | Shared Memory Pools | Cross-process shared pools for IPC buffers | Sprint 1-8, M-03 |
| Sprint 10 | Production Hardening | Benchmark alloc/free latency, fuzz allocation patterns, verify no leaks | All prior |

## 8.07  M-07 Job Engine

Task scheduling with DAG execution, priority queues, and work stealing.

| Sprint | Title | Details | Dependencies |
| --- | --- | --- | --- |
| Sprint 1 | Job Queue | Priority queue, Job struct with dependencies, submit/cancel API | M-01, M-06 |
| Sprint 2 | DAG Execution | Directed acyclic graph of jobs, topological execution order | Sprint 1 |
| Sprint 3 | Worker Pool | Thread pool with configurable size, work stealing between threads | Sprint 2 |
| Sprint 4 | Job Dependencies | Wait-for semantics, barrier jobs, job groups | Sprint 2 |
| Sprint 5 | Resource Requirements | Jobs declare memory/CPU/capability requirements, scheduler validates | Sprint 1-4, M-06 |
| Sprint 6 | Job Persistence | Survive runtime restart, durable job queue | Sprint 5, M-04 |
| Sprint 7 | Distributed Jobs | Submit jobs to remote Astra nodes, result aggregation | Sprint 6, M-13, M-15 |
| Sprint 8 | Priority Inheritance | Prevent priority inversion, deadline-based scheduling | Sprint 3 |
| Sprint 9 | Job Metrics | Track completion time, queue depth, throughput via EventBus | Sprint 1-8, M-09, M-17 |
| Sprint 10 | Production Hardening | Stress test with 10K+ concurrent jobs, verify no deadlocks | All prior |

## 8.08  M-08 AI Scheduler

Machine learning-based resource scheduling and anomaly detection.

| Sprint | Title | Details | Dependencies |
| --- | --- | --- | --- |
| Sprint 1 | Feature Collection | Gather CPU/memory/IO metrics as feature vectors | M-01, M-09, M-17 |
| Sprint 2 | Scheduling Model | Lightweight neural network for scheduling decisions, ONNX runtime | Sprint 1 |
| Sprint 3 | Training Pipeline | Online learning from runtime metrics, model updates without restart | Sprint 2 |
| Sprint 4 | Resource Prediction | Predict memory/CPU needs for incoming jobs | Sprint 1-3, M-07 |
| Sprint 5 | Anomaly Detection | Detect abnormal resource usage patterns, alert via EventBus | Sprint 1-4 |
| Sprint 6 | Adaptive Allocation | Adjust allocator tier sizes based on usage patterns | Sprint 5, M-06 |
| Sprint 7 | Process Placement | Optimal NUMA/core placement for processes | Sprint 6, M-16 |
| Sprint 8 | Workload Classification | Classify workloads (CPU-bound, IO-bound, mixed) for policy selection | Sprint 1-7 |
| Sprint 9 | Federated Learning | Share scheduling insights across Astra nodes | Sprint 8, M-15 |
| Sprint 10 | Production Hardening | A/B test ML scheduler vs static, measure improvement | All prior |

## 8.09  M-09 eBPF Telemetry

Kernel-level observability via eBPF programs for syscall tracing and security monitoring.

| Sprint | Title | Details | Dependencies |
| --- | --- | --- | --- |
| Sprint 1 | eBPF Loader | Load and attach eBPF programs, ring buffer for kernel->userspace data | M-01 |
| Sprint 2 | Syscall Tracing | Trace syscall entry/exit, argument capture, latency measurement | Sprint 1 |
| Sprint 3 | Network Monitoring | XDP programs for packet inspection, connection tracking | Sprint 2, M-13 |
| Sprint 4 | Filesystem Monitoring | Track file access patterns, detect unauthorized access | Sprint 3, M-14 |
| Sprint 5 | Security Events | Detect privilege escalation, namespace escape attempts | Sprint 1-4, M-02 |
| Sprint 6 | Performance Counters | Expose CPU/cache/branch metrics via perf_events | Sprint 5, M-17 |
| Sprint 7 | Map Management | eBPF maps for sharing data between programs and userspace | Sprint 1-6 |
| Sprint 8 | Program Verification | Verify eBPF program safety before loading | Sprint 7, M-12 |
| Sprint 9 | Dynamic Tracing | Attach probes to arbitrary functions at runtime | Sprint 1-8 |
| Sprint 10 | Production Hardening | Verify zero overhead when disabled, test with production workloads | All prior |

## 8.10  M-10 WASM Sandbox

WebAssembly execution environment for running untrusted code safely.

| Sprint | Title | Details | Dependencies |
| --- | --- | --- | --- |
| Sprint 1 | WASM Runtime | Compile/execute WASM modules, linear memory management | M-01, M-06 |
| Sprint 2 | Sandbox Boundary | Capability-gated host function imports, memory isolation | Sprint 1, M-02 |
| Sprint 3 | WASI Interface | WASI preview2 support for filesystem, clock, random | Sprint 2, M-14 |
| Sprint 4 | Memory Limits | Per-module memory budgets enforced by allocator | Sprint 3, M-06 |
| Sprint 5 | Module Loading | Dynamic WASM module loading with signature verification | Sprint 4, M-20 |
| Sprint 6 | Host Bindings | Generate Astra API bindings for WASM modules automatically | Sprint 1-5 |
| Sprint 7 | Multi-Module | Module linking, shared memory between WASM modules | Sprint 6, M-03 |
| Sprint 8 | JIT Compilation | Cranelift-based JIT for hot WASM code paths | Sprint 1-7 |
| Sprint 9 | Debugging | DWARF debug info, source-level stepping in WASM | Sprint 8, M-05 |
| Sprint 10 | Production Hardening | Fuzz WASM parser, benchmark execution speed, verify sandbox escape prevention | All prior |

## 8.11  M-11 AQL Query Language

Astra Query Language for runtime introspection and administration.

| Sprint | Title | Details | Dependencies |
| --- | --- | --- | --- |
| Sprint 1 | Lexer/Parser | Tokenizer and recursive descent parser for AQL syntax | M-01 |
| Sprint 2 | Query Planner | Plan execution of queries against runtime state | Sprint 1 |
| Sprint 3 | Basic Queries | SELECT services, processes, capabilities, events | Sprint 2 |
| Sprint 4 | Filters | WHERE clauses, comparison operators, logical combinators | Sprint 3 |
| Sprint 5 | Mutations | UPDATE/DELETE for runtime state (capability revocation, service stop) | Sprint 4, M-01 |
| Sprint 6 | Aggregations | COUNT, SUM, AVG, GROUP BY for metrics queries | Sprint 5 |
| Sprint 7 | Subscriptions | SUBSCRIBE for real-time event streams | Sprint 6, M-01 |
| Sprint 8 | User Functions | User-defined functions in AQL, WASM-backed UDFs | Sprint 7, M-10 |
| Sprint 9 | Distributed Queries | Query across multiple Astra nodes | Sprint 8, M-13, M-15 |
| Sprint 10 | Production Hardening | Fuzz parser, optimize query plans, add query cost limits | All prior |

## 8.12  M-12 Verification Engine

Formal verification of runtime invariants and security policies.

| Sprint | Title | Details | Dependencies |
| --- | --- | --- | --- |
| Sprint 1 | Invariant Framework | Define and check runtime invariants (e.g., capability monotonicity) | M-01 |
| Sprint 2 | Capability Proofs | Verify no permission escalation, derivation chain integrity | Sprint 1 |
| Sprint 3 | State Machine Verification | Verify ProcessState and ServiceState transitions | Sprint 1-2 |
| Sprint 4 | Memory Safety | Verify allocator invariants: no double-free, no use-after-free | Sprint 3, M-06 |
| Sprint 5 | Concurrency Verification | Verify lock ordering, detect potential deadlocks | Sprint 4 |
| Sprint 6 | Policy Language | Define security policies in declarative language, verify compliance | Sprint 1-5 |
| Sprint 7 | Runtime Assertions | Compile-time and runtime assertion framework with proof obligations | Sprint 6 |
| Sprint 8 | Continuous Verification | Run verification checks in background during execution | Sprint 1-7 |
| Sprint 9 | Cross-Module Verification | Verify inter-module contracts and interface compliance | Sprint 8 |
| Sprint 10 | Production Hardening | Benchmark verification overhead, ensure zero false positives | All prior |

## 8.13  M-13 Network Stack

Capability-gated networking with firewall rules and connection tracking.

| Sprint | Title | Details | Dependencies |
| --- | --- | --- | --- |
| Sprint 1 | Socket Abstraction | Capability-gated TCP/UDP sockets, create/bind/listen/connect | M-01 |
| Sprint 2 | Connection Manager | Connection pool, keepalive, automatic reconnection | Sprint 1 |
| Sprint 3 | Firewall Rules | Per-process network policies, allow/deny by IP/port/protocol | Sprint 2, M-02 |
| Sprint 4 | TLS Integration | Mandatory TLS for all external connections, certificate management | Sprint 3, M-18 |
| Sprint 5 | DNS Resolution | Sandboxed DNS resolver, DNS-over-TLS | Sprint 4, M-02 |
| Sprint 6 | Rate Limiting | Per-connection and per-module rate limits | Sprint 5 |
| Sprint 7 | Protocol Handlers | HTTP/2, gRPC, WebSocket protocol handlers | Sprint 1-6 |
| Sprint 8 | Network Monitoring | Connection metrics, bandwidth tracking via eBPF | Sprint 7, M-09 |
| Sprint 9 | Multi-Node Transport | Node-to-node encrypted channels for distributed Astra | Sprint 8, M-15 |
| Sprint 10 | Production Hardening | Fuzz protocol parsers, penetration test network isolation | All prior |

## 8.14  M-14 Virtual Filesystem

Sandboxed filesystem with capability-based access control.

| Sprint | Title | Details | Dependencies |
| --- | --- | --- | --- |
| Sprint 1 | VFS Abstraction | Virtual filesystem tree, path resolution, capability checks | M-01 |
| Sprint 2 | File Operations | Open/read/write/close with capability gating (FS_READ/FS_WRITE) | Sprint 1 |
| Sprint 3 | Overlay Filesystem | Per-process overlayfs, copy-on-write semantics | Sprint 2, M-02 |
| Sprint 4 | Quota Enforcement | Per-module disk space quotas, inode limits | Sprint 3 |
| Sprint 5 | Temporary Filesystem | tmpfs-backed scratch space, automatic cleanup | Sprint 4 |
| Sprint 6 | File Monitoring | inotify integration, file change events via EventBus | Sprint 5, M-09 |
| Sprint 7 | Integrity Checking | File hash verification, detect unauthorized modifications | Sprint 6, M-18 |
| Sprint 8 | Snapshot Support | Filesystem snapshots for checkpoint/restore | Sprint 7, M-04 |
| Sprint 9 | Distributed Filesystem | Shared filesystem across Astra nodes | Sprint 8, M-15 |
| Sprint 10 | Production Hardening | Fuzz path resolution, verify no path traversal escapes | All prior |

## 8.15  M-15 Consensus Engine

Distributed consensus for multi-node Astra deployments.

| Sprint | Title | Details | Dependencies |
| --- | --- | --- | --- |
| Sprint 1 | Raft Foundation | Leader election, log replication, term management | M-01, M-13 |
| Sprint 2 | State Machine | Replicated state machine, apply committed entries | Sprint 1 |
| Sprint 3 | Membership Changes | Dynamic node join/leave, configuration changes | Sprint 2 |
| Sprint 4 | Snapshot Transfer | Transfer state snapshots for catch-up of lagging nodes | Sprint 3, M-04 |
| Sprint 5 | Capability Consensus | Distributed capability creation/revocation across nodes | Sprint 4, M-01 |
| Sprint 6 | Service Discovery | Distributed service registry, cross-node service lookup | Sprint 5, M-01 |
| Sprint 7 | Split Brain Protection | Quorum-based decisions, network partition handling | Sprint 1-6 |
| Sprint 8 | Multi-Raft | Separate Raft groups per module for independent scaling | Sprint 7 |
| Sprint 9 | Byzantine Tolerance | Optional BFT mode for untrusted node environments | Sprint 8 |
| Sprint 10 | Production Hardening | Jepsen-style testing, verify linearizability under partitions | All prior |

## 8.16  M-16 Hardware Abstraction

Hardware detection and CPU feature abstraction layer.

| Sprint | Title | Details | Dependencies |
| --- | --- | --- | --- |
| Sprint 1 | CPU Detection | CPUID parsing, feature flags (AES-NI, AVX2, SHA-NI, etc.) | None |
| Sprint 2 | Memory Topology | NUMA node detection, cache hierarchy mapping | Sprint 1 |
| Sprint 3 | Crypto Acceleration | Detect and dispatch to hardware crypto instructions | Sprint 2, M-18, M-21 |
| Sprint 4 | Power Management | CPU frequency scaling, power state awareness | Sprint 3 |
| Sprint 5 | Device Enumeration | PCI/USB device listing, driver capability detection | Sprint 4 |
| Sprint 6 | Feature Abstraction | Unified API regardless of underlying hardware | Sprint 1-5 |
| Sprint 7 | Performance Counters | Hardware PMC access, cache miss / branch miss tracking | Sprint 6, M-17 |
| Sprint 8 | Heterogeneous Compute | GPU/accelerator detection and offload API | Sprint 7 |
| Sprint 9 | Thermal Monitoring | CPU temperature, throttling detection | Sprint 8 |
| Sprint 10 | Production Hardening | Test on diverse hardware, verify graceful fallback for missing features | All prior |

## 8.17  M-17 Profiler

Runtime profiling, flame graphs, and hotspot analysis.

| Sprint | Title | Details | Dependencies |
| --- | --- | --- | --- |
| Sprint 1 | Sampling Profiler | Periodic stack sampling, call graph construction | M-01, M-09 |
| Sprint 2 | Flame Graphs | Generate flame graph SVGs from profiling data | Sprint 1 |
| Sprint 3 | Memory Profiler | Track allocation patterns, detect leaks, peak usage | Sprint 2, M-06 |
| Sprint 4 | Lock Contention | Measure spinlock wait times, detect contention hotspots | Sprint 3 |
| Sprint 5 | Event Profiler | Profile EventBus dispatch latency, handler execution time | Sprint 4 |
| Sprint 6 | IPC Profiler | Measure IPC latency, message throughput, channel utilization | Sprint 5, M-03 |
| Sprint 7 | Continuous Profiling | Always-on low-overhead profiling with ring buffer | Sprint 1-6 |
| Sprint 8 | Diff Profiling | Compare profiles before/after code changes | Sprint 7 |
| Sprint 9 | Distributed Profiling | Aggregate profiles across Astra nodes | Sprint 8, M-15 |
| Sprint 10 | Production Hardening | Verify <1% overhead, test with production workloads | All prior |

## 8.18  M-18 Crypto Engine

Cryptographic services: TLS, key management, hardware-accelerated algorithms.

| Sprint | Title | Details | Dependencies |
| --- | --- | --- | --- |
| Sprint 1 | Hash Functions | SHA-256/512 with AES-NI/SHA-NI hardware acceleration | M-21 |
| Sprint 2 | Symmetric Encryption | AES-256-GCM, ChaCha20-Poly1305 | Sprint 1, M-21 |
| Sprint 3 | Key Management | Key generation, rotation, secure storage, derivation (HKDF) | Sprint 2 |
| Sprint 4 | TLS 1.3 | Full TLS 1.3 implementation, certificate handling | Sprint 3, M-13 |
| Sprint 5 | Digital Signatures | Ed25519, ECDSA for code/module signing | Sprint 4 |
| Sprint 6 | Secure Random | CSPRNG backed by RDRAND/RDSEED + /dev/urandom | Sprint 5, M-21 |
| Sprint 7 | Key Escrow | Secure key backup, multi-party key recovery | Sprint 6 |
| Sprint 8 | Post-Quantum | Kyber/Dilithium for PQ-safe key exchange and signatures | Sprint 7 |
| Sprint 9 | Crypto Audit | Log all crypto operations, key usage tracking | Sprint 8, M-09 |
| Sprint 10 | Production Hardening | NIST test vectors, side-channel analysis, constant-time verification | All prior |

## 8.19  M-19 Virtual Time

Deterministic time for replay, testing, and simulation.

| Sprint | Title | Details | Dependencies |
| --- | --- | --- | --- |
| Sprint 1 | Time Source | Abstract time source interface, wall clock implementation | M-01 |
| Sprint 2 | Virtual Clock | Deterministic clock that advances only on explicit tick | Sprint 1 |
| Sprint 3 | Timer Subsystem | Capability-gated timers, one-shot and periodic | Sprint 2, M-01 |
| Sprint 4 | Time Warp | Fast-forward/slow-motion execution for testing | Sprint 3 |
| Sprint 5 | Replay Time | Synchronize virtual time with replay log timestamps | Sprint 4, M-05 |
| Sprint 6 | Distributed Time | Hybrid logical clocks for cross-node event ordering | Sprint 5, M-15 |
| Sprint 7 | Time Zones | Timezone-aware time formatting and conversion | Sprint 6 |
| Sprint 8 | Monotonic Guarantees | Ensure time never goes backwards, even across NTP jumps | Sprint 7 |
| Sprint 9 | Scheduled Events | Cron-like scheduling within virtual time | Sprint 8, M-07 |
| Sprint 10 | Production Hardening | Verify time monotonicity, test determinism in replay mode | All prior |

## 8.20  M-20 Module Loader

Dynamic module loading with signature verification and hot-reload.

| Sprint | Title | Details | Dependencies |
| --- | --- | --- | --- |
| Sprint 1 | Shared Object Loading | dlopen/dlsym-based module loading, symbol resolution | M-01 |
| Sprint 2 | Module Interface | Standard module entry point, version negotiation | Sprint 1 |
| Sprint 3 | Signature Verification | Verify module signatures before loading (Ed25519) | Sprint 2, M-18 |
| Sprint 4 | Dependency Resolution | Resolve module dependencies, detect version conflicts | Sprint 3 |
| Sprint 5 | Hot Reload | Unload and reload module without runtime restart | Sprint 4 |
| Sprint 6 | Sandboxed Loading | Load modules in isolated namespace, limit symbol access | Sprint 5, M-02 |
| Sprint 7 | Module Registry | Remote module repository, download and verify | Sprint 6, M-13 |
| Sprint 8 | Version Management | Side-by-side module versions, gradual rollout | Sprint 7 |
| Sprint 9 | WASM Modules | Load WASM modules alongside native modules | Sprint 8, M-10 |
| Sprint 10 | Production Hardening | Fuzz module loading, verify no symbol hijacking | All prior |

## 8.21  M-21 Assembly Core

x86-64 assembly implementations for security-critical operations.

| Sprint | Title | Details | Dependencies |
| --- | --- | --- | --- |
| Sprint 1 [DONE] | C++ Stubs | Fallback implementations: secure wipe, constant-time compare, RDRAND, lfence | None |
| Sprint 2 | Secure Memory Wipe | Assembly implementation using rep stosb, register clearing, compiler barrier | Sprint 1 |
| Sprint 3 | Constant-Time Compare | Assembly cmov-based byte comparison, no branches on secret data | Sprint 2 |
| Sprint 4 | RDRAND/RDSEED | Hardware random number generation with retry loops and health checks | Sprint 3 |
| Sprint 5 | AES-NI | AES-128/256 encrypt/decrypt using hardware AES instructions | Sprint 4, M-18 |
| Sprint 6 | SHA Extensions | SHA-256 using Intel SHA-NI instructions | Sprint 5, M-18 |
| Sprint 7 | Cache Flush | clflush/clflushopt for security-sensitive data eviction | Sprint 6 |
| Sprint 8 | Spectre Mitigation | lfence barriers, retpoline stubs, IBRS/STIBP management | Sprint 7 |
| Sprint 9 | Performance Primitives | CRC32, POPCNT, LZCNT for hot path optimization | Sprint 8 |
| Sprint 10 | Production Hardening | Verify constant-time properties, test on diverse CPUs, benchmark vs C++ | All prior |

# 9. Integration Map & Cross-Module Dependencies

Every module integrates with M-01 Core through the IService interface, ServiceRegistry, and EventBus. Below are the non-trivial cross-module dependencies that must be tested during integration.

| Module | Depends On | Integration Details |
| --- | --- | --- |
| M-02 Isolation | M-01 | Registers as ProcessManager isolation hook; uses CapabilityManager for profile selection |
| M-03 IPC | M-01, M-06 | Capability-gated channels; shared memory buffers from allocator pools |
| M-04 Checkpoint | M-01, M-06, M-03, M-14 | Snapshots process memory (allocator), IPC state, filesystem state |
| M-05 Replay | M-04, M-09, M-19 | Loads checkpoints, replays syscalls from eBPF log, uses virtual time |
| M-06 Allocator | M-01 | Capability-gated allocation; quota enforcement per module |
| M-07 Job Engine | M-01, M-06, M-03 | Allocates job structs; IPC for distributed jobs; capability for submission |
| M-08 AI Scheduler | M-09, M-17, M-06, M-07 | Consumes metrics for ML model; adjusts allocator and job scheduler |
| M-09 eBPF | M-01, M-02 | Monitors namespace escapes; provides syscall data to event bus |
| M-10 WASM | M-01, M-02, M-06, M-20 | Sandbox boundary via isolation; memory from allocator; loaded by module loader |
| M-11 AQL | M-01 | Queries runtime state via ServiceRegistry, EventBus, ProcessManager |
| M-12 Verification | M-01, M-06 | Verifies capability invariants; checks allocator safety properties |
| M-13 Network | M-01, M-02, M-18 | Capability-gated sockets; network namespace integration; TLS |
| M-14 VFS | M-01, M-02, M-18 | Capability-gated file access; mount namespace integration; integrity checks |
| M-15 Consensus | M-01, M-13, M-04 | Distributed capability management; network transport; state snapshots |
| M-16 HAL | M-21 | Dispatches to ASM Core for hardware-specific instructions |
| M-17 Profiler | M-01, M-09, M-06 | Samples via eBPF; tracks allocator metrics; EventBus integration |
| M-18 Crypto | M-21, M-01 | Uses ASM Core for hardware crypto; capability-gated key operations |
| M-19 Virtual Time | M-01, M-05 | Runtime time source; replay integration for deterministic time |
| M-20 Module Loader | M-01, M-18, M-02 | Signature verification; sandboxed loading; capability for load |
| M-21 ASM Core | None | Foundation layer — no dependencies |

# 10. Implementation Order (Phased Roadmap)

Modules are built in phases, where each phase unlocks the next. Within a phase, modules can be developed in parallel. Integration testing happens at the end of each phase.

| Phase | Modules | Status | Goal |
| --- | --- | --- | --- |
| Phase 1 | M-21 ASM Core, M-01 Core | COMPLETE | Foundation: crypto primitives, capability model, service registry, process manager, event bus |
| Phase 2 | M-01 Phase 2 (hooks, deps), M-02 Isolation Sprint 1 | COMPLETE | Extensibility: hook registry, dependency graph, namespace sandboxing |
| Phase 3 | M-06 Allocator (Sprint 1-3), M-03 IPC | COMPLETE (M-06), PARTIAL (M-03) | Memory + Communication: pool allocator with security, zero-copy IPC channels |
| Phase 4 | M-02 Sprint 2-4, M-09 eBPF, M-21 Sprint 2-5 | NEXT | Hardening: seccomp, Landlock, cgroups, kernel tracing, real asm implementations |
| Phase 5 | M-13 Network, M-14 VFS, M-18 Crypto | PLANNED | Infrastructure: capability-gated I/O, TLS, filesystem |
| Phase 6 | M-04 Checkpoint, M-05 Replay, M-19 Virtual Time | PLANNED | Persistence: state snapshots, deterministic replay, virtual time |
| Phase 7 | M-07 Job Engine, M-12 Verification | PLANNED | Scheduling + Safety: task execution, formal verification |
| Phase 8 | M-10 WASM, M-20 Module Loader, M-16 HAL | PLANNED | Extensibility: WebAssembly, dynamic loading, hardware abstraction |
| Phase 9 | M-08 AI Scheduler, M-17 Profiler, M-11 AQL | PLANNED | Intelligence: ML scheduling, profiling, query language |
| Phase 10 | M-15 Consensus, all Sprint 10 (Production Hardening) | PLANNED | Distribution + Polish: multi-node, stress testing, formal verification |

## Integration Testing Between Phases

After each phase, run a full integration test that exercises all completed modules together. Key integration tests:

Phase 3->4: Allocate memory via AllocatorService with capability token from Core, verify quota enforcement.

Phase 4->5: Spawn isolated process, allocate memory inside sandbox, communicate via IPC, trace with eBPF.

Phase 5->6: Network connection with TLS, file I/O with capability checks, all traced by eBPF.

Phase 6->7: Checkpoint a running process with IPC state, restore it, verify replay determinism.

Phase 7->8: Schedule jobs that spawn WASM modules loaded by ModuleLoader, verify sandboxing.

Phase 8->9: AI scheduler adjusts allocator based on profiler data, query runtime via AQL.

Phase 9->10: Full distributed scenario — multi-node with consensus, all modules active.

# 11. What Remains To Be Built

## Immediate Next Steps (Phase 4)

M-02 Isolation Sprint 2: Seccomp BPF integration with per-profile syscall filters.

M-02 Isolation Sprint 3: Landlock filesystem access control.

M-02 Isolation Sprint 4: Cgroup v2 resource limits (memory, CPU, PIDs).

M-21 ASM Core Sprint 2: Real x86-64 assembly for secure memory wipe (rep stosb).

M-21 ASM Core Sprint 3: Real assembly constant-time compare (cmov-based).

M-09 eBPF Sprint 1: eBPF program loader and ring buffer for kernel events.

M-03 IPC Sprint 3-4: Send/receive with futex signaling, capability gating.

Complete M-06 Allocator Sprint 4-5: Slab allocator and huge page support.

## Modules Not Yet Started (17 of 21)

M-04 Checkpoint, M-05 Replay, M-07 Job Engine, M-08 AI Scheduler, M-10 WASM Sandbox, M-11 AQL Query Language, M-12 Verification Engine, M-13 Network Stack, M-14 Virtual Filesystem, M-15 Consensus Engine, M-16 HAL, M-17 Profiler, M-18 Crypto Engine, M-19 Virtual Time, M-20 Module Loader have no implementation yet. M-03 IPC and M-09 eBPF have partial implementations.

## Infrastructure Needed

GitHub Actions CI/CD: Build matrix (GCC 13, Clang 17), sanitizer runs, test reporting.

Code coverage tracking (gcov/llvm-cov) with minimum threshold enforcement.

Clang-tidy and clang-format configuration for automated code quality.

Fuzz testing infrastructure (libFuzzer corpus, OSS-Fuzz integration).

Performance regression testing with benchmark suite.

Documentation generation (Doxygen or similar).

Release automation and versioning.

# 12. Critical Context for New Sessions

This section contains everything a new Claude session needs to continue development on Astra without losing context.

## Repository

| Key | Value |
| --- | --- |
| URL | https://github.com/KernelArch-Lab/Astra |
| Branch | main |
| Last Commit | 8cf4c98 — fix(M-06): audit event types, underflow tracking |
| Clone | git clone https://github.com/KernelArch-Lab/Astra.git |

## Team Members

| Name | Role | Contributions |
| --- | --- | --- |
| Shiva | Project Owner & Lead | Architecture, M-01, M-02, M-06, code review |
| Laakhi | Contributor | Initial implementation (Branch-Laakhi) |
| Srivatsan K | Contributor | M-03 IPC Engine (m03-ipc-engine-srivatsan_k branch) |

## Development Environment

| Item | Detail |
| --- | --- |
| Primary Dev Machine | Mac with GCC 13+ / Clang 17+ |
| Cowork VM | Ubuntu 22.04 ARM, g++11 (needs C++17 shims for tests) |
| Build | cmake -B build && cmake --build build -j$(nproc) |
| Test | cd build && ctest --output-on-failure |
| C++ Standard | C++23 (production), C++17 (test shims on older compilers) |
| std::expected shim | /tmp/shim2/expected (for g++11 environments) |

## Naming Convention (MUST follow)

m_ = member, l = local, a = argument. Type: I=int, U=unsigned, B=bool, P=pointer, E=enum, Sz=string, Arr=array, Fn=function, V=vector, R=reference, C=char, F=float, D=double.

## Commit Message Format

type(scope): description. Types: feat, fix, refactor, test, docs, chore. Scope: M-XX module identifier. Example: feat(M-06): Sprint 3 — Per-module quotas. IMPORTANT: No Co-Authored-By Claude line — only Shiva's name in commits.

## Known Issues & Gotchas

Cowork VM has g++11 which lacks C++23. Use C++17 polyfill shim for std::expected when building tests there.

GitHub remote URL: use KernelArch-Lab (no trailing 's'). KernelArch-Labs (with 's') is a different org.

CapabilityToken must be zero-initialized (CapabilityToken lToken{};) to avoid UB with -O2.

npm may be blocked by VM proxy. Use pip install python-docx for document generation.

Allocator tests are C++17 standalone (no dependency on production libs) so they compile on g++11.

ProcessManager spawn requires real Linux privileges (CAP_SYS_ADMIN) for namespace tests.

QuotaManager release() tracks underflows — releasing more bytes than held indicates a bug.

## Last Work Completed

M-06 Allocator Sprint 3 complete with code review fixes applied. All 251 assertions pass across 3 sprint test suites (65 + 72 + 114). Bug fixes: added CAPABILITY_REJECT and POOL_EXHAUSTED audit event types, quota underflow tracking, foreign pointer counter reset on re-init, zero-initialized CapabilityToken in tests. Commit 8cf4c98 pushed to main.